VERRA

Execution Plan & Figma Build Plan

# Verra — Execution Plan

Roadmap, team, architecture & design/Figma build plan

| Document | Execution Plan + Figma Build Plan |
| --- | --- |
| Product | Verra (working name) |
| Version | 0.1 — Draft |
| Date | 16 June 2026 |
| Horizon | ~18 months |
| Companion files | BRD, PRD, clickable prototype |

Table of Contents

# 1. Purpose

This document is the execution plan for Verra: how the product gets built and shipped, the team and timeline, the design/Figma build plan, the technical approach, and the launch checklist. It complements the BRD (why) and PRD (what) with the how and when.

# 2. Delivery Approach

- Design-partner-led: build with 10–15 firms and a few company finance teams shaping the MVP.

- Thin vertical slice first: one jurisdiction (US), one domain (tax), end-to-end, then widen.

- Eval-gated releases: accuracy regression suite must pass before each ship.

- Human-in-the-loop from day one: approval gates and audit log are MVP, not later.

# 3. Phased Roadmap & Timeline

| Phase | Weeks | Key deliverables | Exit criteria |
| --- | --- | --- | --- |
| 0 · Discovery & design | 1–8 | Research synthesis, flows, design system, Figma library, architecture, design-partner LOIs | Signed-off designs + 8–10 LOIs |
| 1 · MVP Tax (US) | 9–24 | Ingestion/parsing, tax analysis, scenarios, reports, assistant, digest, trust layer | Private beta; ≥90% plans accepted w/ minor edits |
| 2 · Beta expansion | 25–36 | Books & Close, Compliance calendar, UK + India, client portal | 10–15 firms live; 3 company teams |
| 3 · GA v1 | 37–48 | Audit module, e-sign, SOC 2 Type II, billing | General availability |
| 4 · Scale v2 | 49–72 | More jurisdictions, direct e-file, integrations marketplace, enterprise (SSO/SCIM) | Enterprise readiness; expansion revenue |

# 4. Workstreams

| Workstream | Scope |
| --- | --- |
| Product & Design | Flows, design system, Figma library, prototype → production specs, usability testing |
| Frontend | Web app (assistant, digest, tax workspace, portals), design-system components |
| Backend & Platform | Multi-tenant services, auth/RBAC, audit log, orchestration, integrations |
| AI / ML | Retrieval, parsing/OCR, agents, deterministic tax calculators, eval suite, model routing |
| Data & Tax Logic | Jurisdiction rules/forms/deadlines, tax-year versioning, calculators |
| Security & Compliance | SOC 2/ISO 27001, privacy (GDPR/DPDP), pen tests, data residency |
| GTM | Design-partner program, pricing/packaging, onboarding, support, marketing site |

# 5. Team & Roles (lean build)

| Role | Count | Focus |
| --- | --- | --- |
| Product Manager | 1 | Roadmap, requirements, design-partner discovery |
| Product Designer | 1–2 | Design system, flows, Figma, usability |
| Frontend Engineers | 2–3 | Web app & components |
| Backend Engineers | 2–3 | Platform, integrations, audit log |
| AI/ML Engineers | 2 | Retrieval, parsing, agents, evals |
| Tax/Domain Expert(s) | 1–2 | Jurisdiction logic, accuracy review (CPA/CA) |
| Security/Compliance | 0.5–1 | Certifications, governance |
| Eng lead / founder | 1 | Architecture, hiring, delivery |

# 6. Technical Architecture (summary)

- Multi-tenant SaaS: strict tenant isolation; RBAC; SSO/SCIM.

- Ingestion pipeline: upload + connectors → OCR/parse → structured extraction with citations + confidence → client profile.

- AI orchestration: retrieval over tenant data; specialized agents; deterministic calculators for bracket/threshold math; model routing for cost.

- Trust layer: immutable audit log, approval-gate service, action receipts, rollback.

- Integrations: QuickBooks/Xero, Plaid, Google/M365, CRM, filing gateways (MeF/GSTN/Companies House).

- Data: per-jurisdiction residency; encryption; zero-retention model contracts.

# 7. Design System & Figma Build Plan

The clickable HTML prototype (verra-prototype.html) is the source of truth for look-and-feel, modeled on ideation. Once the Figma desktop app + Dev Mode MCP are connected, build the Figma file in this order:

## 7.1 Build order

- Foundations / variables: color tokens (accent #5566FF, gradient #8A92FF→#4F46E5, ink #111114, cream #F5F5F5), type scale (Archivo display, Inter body, Fraunces serif), radius (8–22), spacing, shadows.

- Core components: buttons (black pill, periwinkle CTA, ghost), assistant card + mode chips, suggestion row, nav item, KPI card, list/feed row, table, tag/pill, calendar cell, glass insight card, stepper.

- Marketing frames: hero (sky gradient + grid), feature/digest section, stats band, tax dashboard section, STEP 1–4 workflow, personas, security, pricing (3 tiers).

- App frames: Home/Digest, Assistant, Clients/Entities, Tax Planning (scenario compare), Books & Close, Audit workpaper, Compliance calendar, Trust & Audit Log, Settings.

- Variants & states: hover/active/disabled, persona variants (firm/company/individual), light theme; prototype links between frames.

- Handoff: annotate tokens and component props; export for the design-handoff/engineering spec.

## 7.2 Connecting Figma

- Open the Figma desktop app and sign in (Dev or Full seat, paid plan).

- Create/open the target Figma file; with nothing selected, switch to Dev Mode and enable the MCP server in the right sidebar.

- Authorize the Figma connector in Cowork; keep the file open and focused while frames are generated.

Color and type are bound to variables so light/dark and rebrands are one-switch changes; components use auto-layout to match the prototype's responsive behavior.

# 8. Risks & Dependencies (delivery)

| Risk / dependency | Mitigation |
| --- | --- |
| Tax-logic accuracy by jurisdiction | Deterministic calculators + CPA/CA review + eval suite; launch 1 jurisdiction first |
| Model cost at scale | Model routing, caching, batch; usage budgets |
| Integration availability | Start with QuickBooks/Xero/Plaid; abstract a connector layer |
| Security certification lead time | Start SOC 2 readiness in Phase 1; pen-test before GA |
| Design-partner availability | Recruit early; structure with clear value + cadence |

# 9. Launch Checklist (GA)

- Eval suite green for supported jurisdictions/tax years.

- SOC 2 Type II achieved; pen test remediated; DPA & disclaimers in place.

- Approval gates + audit log verified end-to-end.

- Onboarding, docs, support, billing, status page live.

- Design-partner references and ROI case studies captured.

# 10. Immediate Next Steps (2 weeks)

- Confirm jurisdiction order (US → UK or India) with design-partner signal.

- Finalize design system and build the Figma library (once connected).

- Stand up ingestion + tax-analysis spike on real anonymized 1040s.

- Recruit 8–10 design-partner firms; sign LOIs.

- Define the accuracy eval set and target thresholds.

Disclaimer. Concept document; “Verra” is a working name; timelines and figures are indicative for planning.